## User Stories
| Class | CST-247
| Developers | Jay Wilson Chase Hausman Jackie Adair Nathan Ford Richard Boyd
| Description | Minesweeper Web Application Scrum
| Date | 2019-02-17
User Stories |  | Acceptance Criteria
As the user, I want to be able to enter my user name and password so that I can access the application. |  | User can access the application with their username and password.
As the user, I want to be able to register for the system so I that I can access the web application. |  | User can register for an account to the web application.
As the user, I want to be able to play Minesweeper. |  | User can login and play minesweeper.

## Product Backlog
| Class | CST-247
| Developers | Jay Wilson Chase Hausman Jackie Adair Nathan Ford Richard Boyd
| Description | Minesweeper Web Application Scrum
| Date | 2019-02-17
Minesweeper Release Projections
2019-02-18 | Project start
2 | Sprint length (days)
2 | Release 1 sprints (#)
2 | Release 1 release sprint length (days)
2019-02-24 | Release 1 date
2 | Release 2 sprints (#)
3 | Release 2 release sprint length (days)
2019-03-03 | Release 2 date
2 | Release 3 sprints (#)
3 | Release 3 release sprint length (days)
2019-03-10 | Release 3 date
2 | Release 3 sprints (#)
3 | Release 3 release sprint length (days)
2019-03-17 | Release 3 date
2 | Release 3 sprints (#)
3 | Release 3 release sprint length (days)
2019-03-24 | Release 3 date
2 | Release 3 sprints (#)
3 | Release 3 release sprint length (days)
2019-03-31 | Final Release
Minesweeper Product Backlog | [5 empty] | Running | Sprint | Release | Release
ID | Title | Description | Acceptance Criteria | Type | Size (Fib) | Total | Completed | Dates | Goals
1 | Registration Form | As a user, I can create a new user account. | When I create an account, I can login to the service. | Requirement | 20 | 20
2 | Login Form | As a validated user, I want to login to the service. | When I login, my credentials are validated and I am granted access. | Requirement | 11 | 11 |  | 2019-02-24 | Release 1: Registration and Login Forms
3 | Minesweeper Game | As a validated user, I want to play minesweeper. | When I login, I can play minesweeper. | Requirement | 34 | 34 |  | 2019-03-03 | Release 2: Minesweeper Gameboard
Note on A6: Instructions: Update the portion in <> with your product's name.
Note on A8: Instructions (not required): Insert the project start date.
Note on A9: Instructions (not required): Enter the sprint length, in multiples of 7 days per week of sprint.
Note on A10: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A11: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A13: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A14: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A16: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A17: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A19: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A20: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A22: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A23: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A25: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A26: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A29: Instructions: Update the portion in <> with your product's name.
Note on A30: Instructions: Enter the ID of the product backlog item (PBI). The ID usually reflects when it was entered in the system, not the priority. The order of the PBIs indicates the priority. This applies to all cells in this column.
Note on B30: Instructions: Enter the title of the product backlog item. Applies to all cells in this column.
Note on C30: Instructions: Enter the product backlog item description. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on D30: Instructions: Enter the product backlog item acceptance criteria. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on E30: Instructions: Select what type of product backlog item this is (Applies to all cells in this column): Requirement: Typically a user story--work that needs to be done to generate functionality for the user. Improvement: Action items from the sprint retrospective. Maintenance: Development work that neesd to be done on the system, but doesn't create new functionality.. Overhead: Non-development work that needs to be done, but doesn't add direct value to the user.
Note on F30: Instructions: Enter the Fibonacci size estimate assigned by the development team. Applies to all cells in this column.
Note on H30: Instructions: Enter the number of the sprint when the PBI was completed (done).Enter whole numbers to match the format of what appears in F6:F15 above. Applies to all cells in this column.
Note on I30: Instructions (optional): Update any cell below to point to the date generated in A4:A14 indicating the projected release date. Note: This may change as velocity changes.
Note on J30: Instructions (optional): Update <> with the actual release goal.

## Sprint 1 Backlog and Burndown
| Class | CST-247
| Developers | Jay Wilson Chase Hausman Jackie Adair Nathan Ford Richard Boyd
| Description | Minesweeper Web Application Scrum
| Date | 2019-02-24
Minesweeper - Sprints
Sprint Dates: February 25 - March 3, 2019
[6 empty] | Available working hours in the sprint |  |  |  | Days in sprint: | 4.5
[7 empty] | M | Tu | W | Th | F | Total
[6 empty] | Developers | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Review + Retrospective
[6 empty] | Jay Wilson | 3 | 4 | 3 | 2 | 2 | 14
[6 empty] | Chase hausman | 3 | 3 | 3 | 3 | 2 | 14
[6 empty] | Jackie Adaire | 3 | 3 | 3 | 3 | 2 | 14
[6 empty] | Nathan Ford | 2 | 2 | 2 | 2 | 2 | 10
[6 empty] | Richard Boyd | 2 | 2 | 2 | 2 | 2 | 10
[11 empty] | Total sprint hours: | 62
[11 empty] | Total per day: | 13.7778
Feature Burndown - Based on estimated hours remaining
[7 empty] | M | Tu | W | Th | F
ID | Task | Description | Acceptance Criteria | Type | Story Points | Responsible | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Review + Retrospective | Done (Y) | Accepted (Y/N)
1 | Registration Page | As a user, I want to create an account. | When I create an account, I can login to the service. | Requirement | 20 | All | 20 | 20 | 20 | 20 | 20 | Y
| Create registration model | User model to complete registration form. | Model must contain: First Name, Last Name, Gender, Age, State, Email, Username, and Password | Required | 5 | Richard Boyd | 5 | 4 | 3 | 2 | 0
| Create registration form page. | Presentation of form. | All User Model fields functioning and validated properly. | Required | 3 | Nathan Ford | 3 | 2 | 2 | 1 | 0
| Create Registration Controller | Controller to complete the Registration form. | Controller must connect Registration Form to additional connected forms (success / error) | Required | 4 | Jay Wilson | 4 | 4 | 3 | 1 | 0
| Build Serverside Validation | Validation for user signup. | Server-side validation of user credentials. | Required | 2 | Chase Hausman | 2 | 2 | 1 | 1 | 0
| Build SQL Server Database | Database to contain user information. | Relational database built in SQL Server containing all user details as outlined by User Model. | Required | 2 | Jackie Adaire | 2 | 2 | 1 | 1 | 0
| Create Database Service | Service to access database from Controller. | Service accesses and contains all necessary SQL statements usable by any calling controller. | Required | 4 | Jay Wilson | 4 | 4 | 3 | 2 | 0
2 | Login Form | As a validated user, I want to login to the service. | When I login, my credentials are validated and I am granted access. | Requirement | 11 | All | 11 | 11 | 11 | 11 | 11 | Y
| Build Login Controller | Controller to validated user. | Controller to access the database service and validates the user's credentials. | Required | 4 | Jay Wilson | 4 | 3 | 3 | 1 | 0
| Build Login Form | Presentation of form. | Username and password accepted and all items hooked to controllers for access control. | Required | 3 | Chase Hausman | 3 | 2 | 2 | 1 | 0
| Build Login Database Service | Controller to access database for login Controller. | Controller accesses the database and retrieves information for validation. | Required | 4 | Jackie Adaire | 4 | 4 | 4 | 1 | 0
Actual Hrs Remaining | [6 empty] | 31 | 27 | 22 | 11 | 0
Schedule Hrs Remaining | [6 empty] | 31 | 23.25 | 15.5 | 7.75 | 0
[6 empty] | Day: | 1 | 2 | 3 | 4 | 5
Issues
Team Member
N/A

## Sprint 2 Backlog and Burndo (2)
| Class | CST-247
| Developers | Jay Wilson Chase Hausman Jackie Adair Nathan Ford Richard Boyd
| Description | Minesweeper Web Application Scrum
| Date | 2019-02-24
Minesweeper - Sprints
Sprint Dates: February 18 - February 24, 2019
[6 empty] | Available working hours in the sprint |  |  |  | Days in sprint: | 4.5
[7 empty] | M | Tu | W | Th | F | Total
[6 empty] | Developers | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Review + Retrospective
[6 empty] | Jay Wilson | 4 | 2 | 2 | 4 | 2 | 14
[6 empty] | Chase hausman | 5 | 3 | 4 | 4 | 2 | 18
[6 empty] | Jackie Adaire | 6 | 3 | 4 | 5 | 3 | 21
[6 empty] | Nathan Ford | 2 | 2 | 2 | 3 | 4 | 13
[6 empty] | Richard Boyd | 2 | 3 | 2 | 3 | 5 | 15
[11 empty] | Total sprint hours: | 81
[11 empty] | Total per day: | 18
Feature Burndown - Based on estimated hours remaining
[7 empty] | M | Tu | W | Th | F
ID | Task | Description | Acceptance Criteria | Type | Story Points | Responsible | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Review + Retrospective | Done (Y) | Accepted (Y/N)
1 | Create Minewseeper Board | As a user, I want to play Minesweeper | When I login, I can play minesweeper. | Requirement | 27 | All | 27 | 27 | 27 | 27 | 27
| Create View | Build View | View must interact with user. | Required | 3 | Richard Boyd | 3 | 3 | 3 | 3 | 3
| Create Game Board | Build Game Board class. | Gameboard must provide basic game view ofboard. | Required | 8 | Nathan Ford | 8 | 8 | 8 | 8 | 8
| Create Game Logic | Build Game Logic | Game logic class must handle all items related to game logic. | Required | 9 | Jay Wilson | 9 | 9 | 9 | 9 | 9
| Build Controls | Build controls. | Build controls for the game board to use logic. | Required | 7 | Chase Hausman | 7 | 7 | 7 | 7 | 7
Actual Hrs Remaining | [6 empty] | 27 | 24 | 16 | 4 | 0
Schedule Hrs Remaining | [6 empty] | 27 | 20.25 | 13.5 | 6.75 | 0
[6 empty] | Day: | 1 | 2 | 3 | 4 | 5
Issues
Team Member
N/A

## Sprint 3 Backlog and Burndown
| Class | CST-247
| Developers | Jay Wilson Chase Hausman Jackie Adair Nathan Ford Richard Boyd
| Description | Minesweeper Web Application Scrum
| Date | 2019-02-24
Minesweeper - Sprints
Sprint Dates: February 18 - February 24, 2019
[6 empty] | Available working hours in the sprint |  |  |  | Days in sprint: | 4.5
[7 empty] | M | Tu | W | Th | F | Total
[6 empty] | Developers | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Review + Retrospective
[6 empty] | Jay Wilson | 4 | 2 | 2 | 4 | 2 | 14
[6 empty] | Chase hausman | 5 | 3 | 4 | 4 | 2 | 18
[6 empty] | Jackie Adaire | 6 | 3 | 4 | 5 | 3 | 21
[6 empty] | Nathan Ford | 2 | 2 | 2 | 3 | 4 | 13
[6 empty] | Richard Boyd | 2 | 3 | 2 | 3 | 5 | 15
[11 empty] | Total sprint hours: | 81
[11 empty] | Total per day: | 18
Feature Burndown - Based on estimated hours remaining
[7 empty] | M | Tu | W | Th | F
ID | Task | Description | Acceptance Criteria | Type | Story Points | Responsible | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Review + Retrospective | Done (Y) | Accepted (Y/N)
1 | Create Minewseeper Board | As a user, I want to play Minesweeper | When I login, I can play minesweeper. | Requirement | 27 | All | 27 | 27 | 27 | 27 | 27
| Finish Game Logic | Build View | View must interact with user. | Required | 3 | All | 3 | 3 | 3 | 3 | 3
Actual Hrs Remaining | [6 empty] | 27 | 27 | 27 | 27 | 27
Schedule Hrs Remaining | [6 empty] | 27 | 20.25 | 13.5 | 6.75 | 0
[6 empty] | Day: | 1 | 2 | 3 | 4 | 5
Issues
Team Member
N/A

## Design Report
| Class | CST-247
| Developers | Jay Wilson Chase Hausman Jackie Adair Nathan Ford Richard Boyd
| Description | Minesweeper Web Application Scrum
| Date | 2019-02-17
User Stories |  | Completed | Issues | On Time?
As the user, I want to be able to enter my user name and password so that I can access the application. |  | Yes | User registration went smoothly, and there seemed to be no other issues related to logging in. | Yes
As the user, I want to be able to register for the system so I that I can access the web application. |  | Yes | There were some issues with getting the views and controllers hooked, but all has been completed on time. | Yes
As the user, I want to be able to play Minesweeper. |  | Next Week | N/A | N/A
Current Diagram |  |  | Class Diagram